## Issue-Log
ISSUE MANAGEMENT LOG
Project Name: |  |  | Snow Asset Managemen Intergration
Project Manager Name: |  |  | Mathew Gallehawk
Project Ref:
ID | Status | Priority | Issue Description | Owner | Estimated Resolution Date | Escalation Needed (Y/N)? | Impact | Actions | Date Identified | Logged By | Actual Resolution/Completion Date | Final Resolution & Follow-on actions
001 | Work In Progress | Low | Some Model names require Hardcoding | Mathew Gallehawk |  | No | On going code support for devices that do not specify an implicit device name. |  | 2023-05-09 | Mathew Gallehawk | Work around | On going support required
002 | Work In Progress | Low | Asset Tag fo phones issue. | Mathew GAllehawk |  | No | Intune report user issued name as device name 'to many devices called iphone for unique field | concaternated username and 'phone' as the output for asset tag field to provide a unique field, | 2023-09-05 | Mathew Gallehawk | work around
003 | Work In Progress | Low | workstation/ laptop - standard/ advanced , category field has hard coded translation, requires maintance for new models. | Mathew Gallehawk |  | No | without ongoing updates to code NEW model devices will be set to either 'Computer' or 'Mobile Handset' for their model category. | Existing models have been mapped in code. Some inteligent filtering based of naming has been put in place for existing devices. i.e hp zfury … = Laptop - Advanced. | 2023-05-09 | Mathew Gallehawk | Work around | on going support or acceptance
004 | Open | Medium | Script requires ongoing maintenance | mathew Gallehawk |  | Yes | ownership of the repsonsibility of maintaining the script must be determined |  | 2023-09-05 | Mathew Gallehawk
005 | Work In Progress | Low | "fields Last logged on and last log on date. Not populating from sccm | Mathew Gallehawk |  | Yes | current work around is functional, involves Sophos. Stake holder requires this to come from microsoft | Tasked Infrastructure with the creating a microsoft bi report to generate this information.RITM0047052 | 2023-05-09 | Mathew Gallehawk
Note on A6: A unique ID number
Note on B6: Status: - Open: The issue is currently open but has not yet been addressed. - Work In Progress: The issue is being actively worked to develop a resolution. - Closed: The issue is no longer considered an active project threat and can be closed with or without resolution.
Note on C6: Critical, High, Medium, Low. Critical: Issue will stop project progress. High: Issue will likely impact budget, schedule or scope. Medium: Issue impact the project, but could be mitigated to avoid an impact on budget, schedule or scope. Low: Issue is low impact and/or low effort to resolve.
Note on D6: Give a brief description of the issue.
Note on E6: The individual most responsible for working towards resolving the issue.
Note on F6: Estimated or target date for completion of actions.
Note on G6: “Yes” if the program/project manager feels an issue needs to be escalated and “No” if escalation is not needed to resolve the issue.
Note on H6: Describe the impact of the issue. This may be in terms of the project constraints of time, cost and scope. See http://www.stakeholdermap.com/project-management/project-triangle.html
Note on I6: Actions to mitigate the issue, avoid the issue or resolve the issue.
Note on J6: The date that the issue was identified.
Note on L6: Actual completion date.
Note on M6: Document the final outcome. Is the issue resolved and if so how? Are there any follow-on actions? Are there any follow-on risks?

## severity-levels
Issue severity | Description
Critical | Issue will stop project progress.
High | Issue will likely impact budget, schedule or scope.
Medium | Issue impact the project, but could be mitigated to avoid an impact on budget, schedule or scope.
Low | Issue is low impact and/or low effort to resolve.