## Slide 1: Snow Asset Management Integration Project
Service Now asset management is not accurately displaying the state of the ICT assets. This affects the accuracy of reporting, as well as creates issues for assigning hardware and tracking assets.
The result of this project, shall update SNOW Asset management on a regular basis to address these issues.
Business Need, Objectives & Benefits
Key Stakeholders
Executive: <GM>
Business Lead: <Mathew Gallehawk>
Contributing Division(s):
<ServiceDesk, Business systems>
Team member: <Name>
Planning Considerations
Delivery Approach / Scope
Estimated Start period
Within 3mths.
Estimated Cost.
Is the internal labor only,
Assumptions
Business Systems will provide ongoing support for the product.
Intune is the primary source of import data.
Solution will be an adaption to a current process.
Dependencies
Incorporation of monitors is reliant on ‘HP Monitors Fleet Management’ project.
Risk
Risk of corrupting data on the current asset management system. Mitigated by testing in the Development environment coupled with peer review and rollback options.
Constraints
Service Desk Duties
Quality of Asset Data / Data Sources
Sprint 1
Prototype script that generates the required output to update Snow Asset Management.
Add functionality to manage Phones and computers.
Add functionality to adjust mandatory fields in snow.
Add error handling and portability.
Sprint 2
Add functionality to include Monitors.
Add functionality to include Headsets
Add functionality to incorporate Ethen Group export
Sprint 3
Add functionality to update Purchase Orders and Costs
Add functionality to include peripherals and other devices from alternative data sources.
Create Training and support material.
Strategic Objectives
Delivery Parameters
Approval Conditions
Will require Change Request. Pending Business Systems peer-review.
> 2M
< 250k
> 24m
< 6m
High
Low
High
Low
Responsibility: <Mathew Gallehawk>
Accountability: <Business systems>
Consulted: <Business systems>
Informed: <Business systems, Service Desk>

## Slide 2: Sprint 1 Overview
Deliverable | Requirements
Create a script that Generates spreadsheets required for Snow. | Script takes in Intune export fields and outputs SNOW bulk upload list and snow model update list Focus is on Phones and Computers for this sprint. Script to create objects of computers and phones from Intune export file.
Add functionality to populate last logged-in and date. | This functionality was formerly supplied by SCCM, has not been populated since the deactivation of SCCM. Not “Required for successful upload to SNOW. Stake holder would prefer this functionality from Microsoft if possible.
Add error handling and portability. | Terminate the app gracefully with an error message if the required export sheets are not present. Clean up old sheets so that old data does not get re-populated. Close all connections to AzureAd on close. Script and required folders should just unpack on a pc and work.
Sprint 2 Overview
Deliverable | Requirements
Integrate Monitors | Confirm corporate or personal device. Assign an asset tag. Match the monitors to users.
Integrate Headsets | Confirm corporate or personal device. Assign an asset tag. Match the monitors to users.
Integrate Ethan Group report | Rationalise data accurately.
Sprint 3 Overview
Deliverable | Requirements
Integrate peripherals | Generate model category for new devices Generate an asset tag Populates all required fields Populates PO and cost
Integrate Network Infrastructure | Generate model category for new devices Generate an asset tag Populates all required fields Populates PO and cost
Integrate Audio Visual equipment | Generate model category for new devices Generate an asset tag Populates all required fields Populates PO and cost
Integrate PO and cost for devices | Populate PO number field for all devices possible. Populate cost field for all devices possible.
Create Training and support material | Document technical support. Document end-user setup and requirements.

## Slide 4: Sprint 1 Testing
The script output files were tested in the Development Snow environment. Results were reviewed by Vijay the technical expert for ServiceNow.
Wins | Losses
Created non-existent hardware models and migrated the incorrectly assigned devices to appropriate fields. | Phone naming is not managed in Intune and will not be unique enough needs addressing. (Mitigated)
Updates records of existing devices in SNOW, not duplicate. | Concerns about the amount of Service Desk support required to map category types of laptop/workstations standard /advanced etc as without updating code new models will either be a Phone or a Computer.
Updating a blank field does not remove existing data. | Still Utilising Sophos to populate “Last Logged in” and “Last Log in date’ fields.
All currently used fields, auto populated fields and Last user and last logged-on fields populate where data is available. | 
Does not upload personal devices or devices that have not deployed correctly. | 
Adds new assets correctly. | 

## Slide 5: Recommendations
Recommendations | Responsibility
Request for approval for Sprint 1 to be deployed to production. Vijay to review testing and move the current code to production “Last Login data” current supply from Sophos for sprint 1 | Business Systems ServiceNow Admin & PowerShell developer
Move continued development to Business systems. Approval for Sprint 2 Approval for sprint 3 | Business Systems ServiceNow Admin & PowerShell developer
Infrastructure to develop solutions to replace Sophos for “last logged-in” fields. Source of truth must be Intune Infrastructure team to supply report with requested data | Infrastructure department