## Slide 1
Cyber Security Awareness
Campaign Plan 2022/23

## Slide 2
Cyber Security Awareness
Campaign Objectives
With an ever-evolving threat landscape we find it critical that we develop and align our enterprise to protect ourselves against Cyber threats.
Failing to do so will put our business in severe risk of being compromised with the potential for large manufacturing outages and safety risks for our machine operators.
Individual user awareness training assists us to mitigate many of the key risks by identifying and dealing with threats in a consistent manner.

## Slide 3
Current Threat levels (March extract)

## Slide 4
Cyber Security Awareness
Campaign Phases
Part 1
Topic: Email/SMS Security
Part 2
Topic: Removable Media
Part 3
Topic: Password and
Authentication
Part 4
Topic: Physical Security
Launch

## Slide 5
October 2022 – Plan approval by GM’s & MD
October 2022 – Campaign Launch & initial awareness / Toolbox talks
Nov-Dec 2022 – Part 1 – Email/SMS Security Simulations & Training
Jan-Feb 2023 – Part 2 – Removable Media
Mar-Apr 2023 – Part 3 – Passwords and Authentication
May-Jun 2023 – Part 4 – Physical Security
Cyber Security Awareness
Campaign Timeline

## Slide 6
Initial
  Preparation
    Management awareness and support for campaign
    Toolbox Talk documents
    Toolbox talk sessions to be conducted
    Lunch and Learn awareness sessions
  Microsoft Defender
    Email Phishing simulations
    Email Ransomware simulations
    Microsoft training
    Results reporting
Later
  USB & Physical security
    Education and exercises
  Management Training
    Situation simulations
Cyber Security Awareness
Key components

## Slide 7: Cyber Security Awareness Campaign Launch

## Slide 8
Oct 20 2022 – Toolbox Talk documents & Training material published on intranet
      Mail message delivery to GM’s & Branch Managers noting times for sessions below
Oct 21 & 24 2022 – Optional session for those delivering Toolbox Talks (ICT Hosted)
Oct 21-30 2022 – Toolbox Talks conducted across the business
Oct 28-30 2022 – Optional Lunch & Learn sessions via Teams (ICT Hosted)
Cyber Security Awareness
Campaign Launch
Note: Samples provided for review – We will publish on intranet

## Slide 9: Email/SMS Security Training

## Slide 10: Microsoft Defender – Data available
Over the sample month, Microsoft Defender detected 183 email threats against G. James employees that made it through Network/end User defences
This is normal mass for Phishing attacks in business at the moment.
Service Desk was alerted to this by employees. We then had the email sender and URLs blocked, then deleted the emails on mass from the organisations mail boxes.
The below graph shows the volume and time frame of these attacks.

## Slide 11: Phishing Simulation
First Month
First month simulation will cover:
What phishing is, and how to detect and react to it?
Why are phishing attacks targeting the business?
What are the dangers of URLs’ (links) in Emails?
Note:
  Training via Toolbox talks will be provided to the employees before the simulation.
  Simulations will be sent to all computer employees.
  No credentials gathered by the simulations are kept but summarised data reported.
Training
Microsoft provides feedback at the end of the simulation, highlighting the elements of the email that should raise suspicion.
Microsoft then assigns the user training. This is sent as an email to their inbox.
The training provided by Microsoft is a concise interactive tutorial and is tailored to the simulation that they have undertaken.

## Slide 12: Credential Harvest Simulations
Planned simulations Adobe & Netflix:
Things to look out for:
Is the email received, warranted or inappropriate?
Are there inconsistencies regarding spelling, logos, URLs’ and email addresses?
Is there an implied sense of urgency portrayed in the email?
Does the URL or email address make sense and is that the address it will link to?
Provide training
Send first Phishing email
Send second Phishing email
Review results
Process:
Training is provided to employees via Toolbox Talks.
Email is sent informing employees of the simulation.
Simulated phishing emails are sent out to employees.
Recipients interacts with the email (or does not).
Users are provided immediate tailored feedback, from the simulation.
Users are assigned training from Microsoft specifically on Phishing awareness.
Week 1
Week 2
Week 3
Week 4

## Slide 13: Key Take Aways for First Month
Employees should learn to scrutinise URLs and email addresses.
Email links within emails should be avoided whenever possible.
Inconsistencies in spelling, logos and addresses give away that the email may be a scam.
Why is this person talking to me? Unsolicited emails or emails that are sent to incorrect email accounts are indicators of Phishing attacks.
What’s the rush? Implied urgency is a technique used to panic the user into doing something they should not.
Employees should delete Phishing emails or inform G.James Service Desk of the email so that they can check the email and block any URLs and clean up emails sent out, if required.
First Month Lessons learnt - by campaign organisers
Creating and running simulations.
Collecting analytics from simulations.
Recipients’ reaction to simulations was ??
Variations we could deploy in future simulations.

## Slide 14: Sample Report - Summary of First Month
Incidents
Over the first month Microsoft Defender detected XXX email threats against G.James employees.
Service Desk received xxx calls regarding these emails.
Service Desk dealt with XXX malicious emails.
The following graph depicts Email threats detected by Microsoft for the first month.
Graph goes here
Training
Over the first month Service Desk has sent two simulations to employees.
Xxx Employees received these emails.
Xxx Employees received training from these emails.
Xxx Employees reported these emails to the service desk.
Xxx Users who have been caught multiple times.
Xxx Users have outstanding training.
* To be included in board pack

## Slide 16: Further Simulations & exercises being planned
Optional Further reading - follows

## Slide 17: Malware / Attachments Simulation
Second Month
Second month simulation will cover:
How are email attachments dangerous?
How can we scrutinize email sender information?
How to start to critically analysing emails to verify authenticity.
Training
Microsoft provides feedback at the end of the simulation, highlighting the elements of the email that should raise suspicion.
Microsoft then assigns the user training. This is sent as an email to their inbox.
The training provided by Microsoft, is a concise interactive tutorial and is tailored to the simulation that they have undertaken.

## Slide 18: Malware Simulations
Planned simulations Facebook and Microsoft:
What to look out for:
Is the email received warranted or inappropriate/unprofessional?
Is this form of installation appropriate for the company?
Are there inconsistencies regarding spelling, logos or URLs and email addresses?
Does the from address make sense?
Does the URLs make sense and is that the address it will link to?
Provide training
Send first Malware email
Send second Malware email
Review results
Week 1
Week 2
Week 3
Week 4
Process:
Training is provided via SharePoint.
Email is sent informing employees of the simulation.
Simulated phishing emails are sent out to employees.
Recipients interacts with the email (or does not).
Users are provided immediate tailored feedback, from the simulation.
Users are assigned training from Microsoft regarding Malware awareness.

## Slide 19: Key Take Aways
Detect and understand attachment extensions.
Do not install or download executables from emails.
Spot inconsistencies in spelling, logos and addresses.
Critically analyse emails for lapses in professionalism and business practices.
Inform G.James Service Desk of the email so that they can clean out malware, block any URL and clean up emails sent out to the company.
Second Month Lessons learnt
Creating and running simulations.
Collecting analytics from simulations.
Recipients’ reaction to simulations was ??
Variations we could deploy in future simulations.

## Slide 20: Overview of Second Month
Incidents
Over the first month Microsoft Defender detected XXX email threats against G.James employees.
Service Desk received xxx calls regarding these emails.
Service Desk dealt with XXX malicious emails.
The following graph depicts Email threats detected by Microsoft for the second month.
Graph goes here
Training
Over the second month Service Desk has sent two simulations to employees.
Xxx Employees received these emails.
Xxx Employees received training from these emails.
Xxx Employees reported these emails to the service desk.
Xxx Users who have been caught multiple times.
Xxx Users have outstanding training.

## Slide 21: Ransomware Simulation
Third Month
Third month simulation will cover:
What is Ransomware and why is it a concern?
How does Ransomware appear on our systems?
What to do if Ransomware is found?
Training
Microsoft provides feedback at the end of the simulation, highlighting the elements of the email that should raise suspicion.
Microsoft then assigns the user training, this is sent as an email to their inbox.
The training provided is a concise interactive tutorial and is tailored to the simulation that they have undertaken.
Note:
G.James must maintain the trust of the employees. To achieve this the training pack will reinforce that:
  Training will be provided to the employees before the simulation.
  Simulations will be sent to all computer employees.
  No credentials gathered by the simulations are kept.

## Slide 22: Simulations
Planned simulations Fake client and Fake bank:
Is the email received warranted or inappropriate/unprofessional?
Does the file or attachment seem suspicious?
Is this form of installation appropriate for the company?
Is the computer behaving strangely?
Random text file has appeared. What to do?
Provide training
Send first Ransomware email
Send second Ransomware email
Review results
Week 1
Week 2
Week 3
Week 4
Process:
Training is provided via SharePoint.
Email is sent informing employees of the simulation.
Simulated phishing emails are sent out to employees.
Recipients interacts with the email (or does not).
User are provided immediate tailored feedback, from the simulation.
Users are assigned training from Microsoft regarding Ransomware awareness.

## Slide 23: Key Take Aways
Understand how email attachments can be deceptive.
Do not install or download executables from emails or the internet.
Knowing how to respond to malware, particularly ransomware.
Third Month Lessons Learnt
Creating and running simulations.
Collecting analytics from simulations.
Recipients’ reaction to simulations was ??
Variations we could deploy in future simulations.

## Slide 24: Overview of Third Month
Incidents
Over the first month Microsoft Defender detected XXX email threats against G.James employees.
Service Desk received xxx calls regarding these emails.
Service Desk dealt with XXX malicious emails.
The following graph depicts Email threats detected by Microsoft for the third month.
Graph goes here
Training
Over the third month Service Desk has sent two simulations to employees.
Xxx Employees received these emails.
Xxx Employees received training from these emails.
Xxx Employees reported these emails to the service desk.
Xxx Users who have been caught multiple times.
Xxx Users have outstanding training.

## Slide 25: Future Months
To be advised as campaign continues