Project Governance

# Project Governance Teams

# Detailed Roles and Responsibilities

A good governance structure does not guarantee good outcomes, but a bad structure will most likely diminish project success!

## What is governance?

- Project Governance is the framework that enables effective project decision making

- The focus is on key decisions that shape the project and its direction

- It has 3 core components within its framework

## Project Governance Framework

- The decision making structure

- The people structure

- The information that informs them

## Strategic Planning and Alignment

Strategic planning and alignment is the process that integrates  strategy, investment, project management, and functional capability to optimize cross-program coordination of all project activities. To accomplish this, a project must provide input to and obtain in-depth knowledge of the Strategic Plan. The objective of this activity is to ensure that the project initiative and related activity is coordinated and integrated with our initiatives.

## Project Methodology

Templates are located in the project folder on the network drive. The foundation pillars to align the governance to the project are:

| 7 Principles | 7 Processes | 7 Themes |
| --- | --- | --- |
| Continual Business Justification | Start Up | Business Case |
| Learn From Experience | Directing | Organisation |
| Defined Roles and Responsibilities | Initiating | Quality |
| Manage By Stages | Controlling | Plans |
| Manage By Exception | Managing Product Delivery | Risk |
| Focus on Products | Managing a Stage Boundary | Change |
| Tailor to Suit | Closing | Progress |

# Table of contents

Contents

Project Governance Teams	1

Detailed Roles and Responsibilities	1

What is governance?	1

Project Governance Framework	1

Strategic Planning and Alignment	1

Project Methodology	1

Table of contents	2

Introduction	3

Purpose	3

Project governance structure	3

Causes of governance problems	4

Team Selection Panel	4

Roles	4

Team Definitions	5

Project Sponsor	5

Role	5

Project Sponsors Responsibilities	5

Steering Team	6

Project Manager	7

Development Team	8

Testing Team	8

Training Team	9

Logistics Team	9

Status Reporting	10

Definition	10

Why is it important?	10

Document Requirements	10

## Introduction

This document explains the project governance teams and responsibilities to deliver projects within the project charter to enable successful delivery of new business capability in a managed and supported environment.

## Purpose

This guideline defines the overall parameters for successful project governance.  It also provides a foundation for the organized and consistent planning and execution of projects. More specifically, this document’s goal is to describe each team’s actual work that is performed during a project.

## Project governance structure

Continual Service Improvement

Functional Teams

Project Review

Logistics

Training

Testing

Development

Project Manager

Steering committee

Project sponsor

## Causes of governance problems

A key objective of governance is to make decisions efficiently, effectively and transparently. Sound governance is not always clearly established resulting in:

failure to communicate fully and appropriately on a timely basis;

failure to specify or accept decision making authority and responsibilities;

indecision, lack of project direction and control;

confusion between the project and organisational decision-making structures;

non-alignment of key stakeholders;

over emphasis on reporting that reduces meetings to status updates rather than interactive decision making;

confusing contract management and decision making; and

failure to sustain governance processes and practices through to delivery of benefits to the organisation.

## Team Selection Panel

All projects will contain a several teams to ensure the end delivery goal of the project is achieved. Projects will vary in size and complexity based on the deliverable required.  This section outlines the teams needed to deliver a project, however selection of the teams needed should be directly proportional to the size and requirements of the project. Following Prince 2 principal of “Tailor to suit”

### Roles

- Project Sponsor – Agree to mandate the project and own the outcome

- Steering Committee – Team to guide the project deliverables and approve the end goal

- Project Manager – Manage the day to day operations and report up and down to project teams

- Project Team – accounts for team members to review status updates

- Development Team – function work to complete tasks associated to the project

- Testing Team – To test functionality of expected project outcomes

- Training Team – To prepare the staff for the delivery of change

- Logistics – To prepare the environment for delivery change

# Team Definitions

## Project Sponsor

### Role

The Project Sponsor is the individual (often a manager or executive) with overall accountability for the project.

The Project Sponsor is primarily concerned with ensuring that the project delivers the agreed business benefits.

The Project Sponsor acts as the representative of the organisation, and plays a vital leadership role through:

- providing 'championship' for the project, selling and marketing the project throughout the organisation

- providing business expertise and guidance to the Project Manager

- acting as the link between the project, the business community and perhaps most importantly, management decision making groups

- acting as an arbitrator and making decisions that may be beyond the authority of the Project Manager

### Project Sponsors Responsibilities

Typically the Project Sponsor will be responsible for:

- ensuring that the business need is valid and correctly prioritised

- ensuring that the project is properly launched

- ensuring that the project remains a viable business proposition

- ensuring changes to the project are properly managed

- ensuring risks are managed

- establishing the project organisation, roles and reporting structure

- ensuring the project is under control

- approving key project deliverables

- initiating project reviews and supporting the process of review

- resolving issues (typically competition for resources and priority clashes) that are beyond the control of the Project Manager

- resolving conflict and removing obstacles to progress

- overall quality of the project, both the methods used to develop it and the end product.

During the life of any project, business circumstances may change considerably, making it impossible for the Project Manager to carry out his/her job. Examples are such things as changes of policy, adverse business conditions, etc.  In such cases the Project Sponsor is responsible for recognising and reacting to any such circumstances.

## Steering Team

The Steering Team’s goal is customer satisfaction. The Steering Team articulates a vision for the product or service, acquires and quantifies high-level customer requirements, develops and maintains the business case, and manages customer expectations. Its role is to ensure that business expectations are clearly articulated and understood by all stakeholders and the other project governance teams and that the functional specification responds to business priorities. The Steering Team must also facilitate the rapid resolution of issues and decisions that cannot be agreed upon or resolved among the other project governance teams. The Steering Team is responsible for ensuring that the project follows a technical, policy and quality standards and procedures. The Steering Team is comprised of staff from all stakeholders including vendor project management staff when appropriate.

The Steering Team has the following roles and responsibilities on a project:

    - Ensure project alignment with overall business objectives

    - Review and sign off on project charter

    - Strategic planning and executive decision point resolution

    - Cross department coordination and stakeholder communication

    - Monitor project risks and next steps

    - Maintain knowledge of project status to apply to executive decisions across business areas

    - Develop, maintain and carryout the business case (concept paper) for the initiative

    - Provide advice and guidance to the other project governance teams

    - Support the Project Management team with resource acquisition

    - Establish overall project requirements and priorities

      - Communicate user needs, define the business problem, identify expected benefits, and manage expectations

      - Outreach to the user community and stakeholders

      - Articulate a project vision (What it is and what it isn’t)

    - Ensure project scope and execution activity is in line with customer requirements and solutions that solve the business problems

- At a minimum, the Steering Team is accountable for the following project deliverables:

  - Creation of justification documents and funding to show why the initiative should be carried out or continued

  - A plan for customer and stakeholder management

  - Formal verification that all policy and mandate requirements have been addressed

  - Development and execution of a formal project communication plan

A detailed description of each Steering Team high-level activity is described below:

| - Strategic Planning and Alignment | - Customer Satisfaction |
| --- | --- |
| - Initiative Justification | - Business Process Re-engineering |
| - Funding | - Business Results |
| - Support Guidance to Other Teams | - Mandate Interpretation |
| - Communications and Status Reporting | - Stakeholder Management |
| - Executive Sponsorship, Support, and Roadblock Elimination |  |

## Project Manager

The project manager drives the critical decisions necessary to release the right product, according to the Steering Team’s direction, at the right time and within the project’s established resource constraints. The project manager clarifies the business case, identifies the detailed project requirements, and integrates the efforts of each functional team described below.

The Project Manager has the following project roles and responsibilities:

- Owns and drives the project schedule, business requirements, application functionality, and budget

- Drives core project level decisions requiring integration across the other project governance teams

- Submits final deliverables to customer and obtains acceptance sign-off

- Manages the project scope and specifications to meet the Steering Team’s requirements

- Identifies tradeoffs between cost, schedule, and deliverable product

- Integrates detailed work plans into one overall project plan

- Develops and executes project quality and configuration management plan

- Manages all subordinate teams’ resources and roles

- Coordinates resources, facilities, and team communication

- Tracks project status against project plans

- Communicates with the Steering Team and the other project governance teams

- Escalates unresolved issues to the Steering Team

- Prepares and distributes status reports

The Project Manager is accountable for the following project documents and concepts:

  - Detailed project work plan and schedule that integrates all project work activity

  - Risk mitigation plan

  - Change Management

  - General System Design (GSD) document

  - Quality Assurance plan

  - Status reports

  - Documentation of changes to baselined control items

  - Requirements Definition

  - Scope Management

## Development Team

The Development Team designs and implements a quality product or service that meets the specification and customer expectations. Development should focus on the functional specification and on meeting customer expectations.

The Development Team has the following roles and responsibilities on a project:

- Design and build product to requirements specification

- Validate potential solutions through input to design, technology evaluations and proof-of- concept prototypes

- Estimate time and effort to complete the design and product build

- Develop, configure and customize the product

- Serve as technical consultants

- Support the product installation and deployment

- At a minimum, the Development Team is accountable for the following project deliverables:

  - Detailed System Design (DSD)

  - Interface and exchange capabilities, utilities and tool sets

  - Converted data from the system that is being replaced, where required

## Testing Team

The Testing Team ensures all issues are known before the product or service’s release. This role must be independent of development to be truly effective. Testing provides independent product quality verification and validation in relation to baseline specifications.

The Testing Team evaluates and integrates the product and deliverables and determines whether project requirements have been satisfied.

The Testing Team has the following roles and responsibilities on a project:

  - Early involvement to gain a clear understanding of user’s needs and how the product will meet the needs

  - Review and validate the project deliverables’ quality

  - Ensure the product conforms to the project’s specifications

  - Technical performance and reliability

  - Participate in the design phase

  - Develop test strategies, plans, and scripts

  - Conduct tests

  - At a minimum, the Testing Team is accountable for the following project deliverables:

    - Detailed test plan

    - Test scripts

Test report confirming project is ready to be moved into production

## Training Team

The  User  Training  Team  enables  users  to  maximize  the  product  or  service  through performance solutions such as job aides, FAQs, online help and education systems.

The User Education Team has the following roles and responsibilities on a project:

  - Act as the advocate for the User of the product

  - Participate in designing the features to ensure that the product is usable and useful

  - Participate in defining user requirements

  - Design and develop user support materials

  - Participate in product prototyping

  - Perform usability testing

  - Ensure that changes in the product are reflected in the support materials

  - At  a  minimum,  the  User  Education  Team  is  accountable  for  the  following  project deliverables:

    - Documented process impacts and change requirements

    - Employee transition plan

    - Training  plan  and  materials  including  outreach  presentations,  online  help,  user manuals, training content, FAQs and job aides

    - Updates to policy and procedures

    - Training delivery

## Logistics Team

The Logistics Team ensures a product or service rolls out, installs, and implements smoothly during the Operations Support Phase.

The Logistics Team has the following roles and responsibilities on a project:

- Serves as advocate for operations, product support, help desk, and product delivery channels

- Participates in design phase

- Supports the product through beta testing

- Ensures that product will be deployable and maintainable

- Ensures product installation site has the appropriate infrastructure

- Provides education and operation to support personnel

- At a minimum, the Logistics Team is accountable for the following project deliverables:

    - Project configuration management plan

    - Security plan

    - Disaster recovery plan

    - Capacity plan

    - Acquisition and configuration of technical environments for development, testing, training and production

    - Installation plan

    - Maintenance and ongoing operation strategy

## Status Reporting

## Definition

Project status reporting is an initiative designed to provide all parties involved with comprehensive, accurate, and informative reports on strategic projects. These reports provide summarized project statuses, release descriptions, planned implementation dates, cross project/program impacts, and business/architectural review board meeting dates. This process provides a forum for project leads to communicate recent statuses and/or events regarding their assigned projects. It also allows for these project leads to learn of statuses and/or events regarding other projects which may impact the project(s) in which they are responsible for.

## Why is it important?

The status reports enable Department executives and project leads to make informed project-related decisions in a timely and efficient manner. Project teams become more aware of the activities of other projects due to the integrated format of the reports. Communication between project teams is enhanced due to weekly status reporting meetings.

## Document Requirements

- Project Governance Document

- Project Charter document

- Project Brief Document

- Business Case Document

- Financial Brief

- Project Plan

- Functional Requirements Document

- Communication Management Plan

- Risk Management Plan

- Project Status Updates

- Issues and Risk log

- Work Package Plan

- End of Stage Reports

- Change Management Plan

- Testing Plan

- Training Plan