## Slide 2: Intune Snow asset Import
By Mathew Gallehawk
For: Darren Daly, Bruce Absolom, Joel Porgand

## Slide 3: I – Asset Management
Consolidate ICT hardware information into SNOW Asset management.
Clean inconsistencies and errors existing in asset data within snow.
Create a simplistic process to maintain accuracy or the SNOW Asset Management Data.
The result will be SNOW Asset management will be an accurate source of truth regarding ICT Asses.
Business Need, Objectives & Benefits
Initial Scope of devices:
Computers
Mobile Phones
Secondary Scope:
Monitors
Tertiary Scope:
Peripherals
Network Infrastructure
Audio Visual equipment
Scope
Key Stakeholders
Executive: <GM>
Business Lead: <Name>
Contributing Division(s): <Engineering>
<Finance>
<ICT>
Team member: <Name>
<Name>
<Name>
<Name>
Planning Considerations
Delivery Approach
Estimated Start period
Within 3mths,.
Estimated Cost.
Is the internal labour only,
Assumptions
Some one will provide ongoing support to solution.
Intune being the primary source of import data.
Solution will be an adaption to a current process.
Dependencies
Incorporation of monitors is reliant on ‘HP Monitors Fleet Management’ project..
Risk
Risk of corrupting data on current asset management system. Mitigated by testing in Development environment coupled with peer review and roll back options.
Constraints
Service Desk Duties
Quality of Asset Data / Data Sources
Sprint 1
Prototype script that generates the required output to update Snow Asset Management.
Add functionality to manage Phones and computers.
Add functionality to adjust mandatory fields in snow.
Add error handling and portability.
Create Training and support material.
Sprint 2
Add functionality to include Monitors.
Add functionality to update Purchase Orders and Costs
Sprint 3
Add functionality to include peripherals and other devices from alternative data sources.
Strategic Objectives
Delivery Parameters
Approval Conditions & Portfolio Fit
Will require Change Request.
Will require process change and training for Service Desk.
> 2M
< 250k
> 24m
< 6m
High
Low
High
Low

## Slide 4: Business Problem
ServiceNow (SNOW) Hardware Asset Management (HAM) is our source of truth for asset management for G.James ICT department.
Asset Management and reporting is hindered by inconsistencies caused by:
Multiple Asset Management systems used within G.James.
Shipping devices straight to customers.
Assets being moved between customers within the branch without Service Desk knowledge.
Retired, missing, duplicate or obsolete assets being present within SNOW HAM.
Duplicate devices present from the migration to Intune.
Proposed Solution
Create a system that exports a log of each of the asset management systems, resolves the fields, and uploads the amended asset list to SNOW HAM.
Desired Outcome of Project
SNOW HAM to accurately reflect the quantity, assignment, and state of hard assets owned and managed by G.James.
ServiceNow (SNOW) Hardware Asset Management system, to be automatically updated from other Asset management Systems utilized by G.James ICT department.
SNOW HAM to Deduplicate devices by serial number or unique key.
Limitations and Considerations
Fields between different asset management systems do not always directly correlate and may require transformation. i.e corporate device = G.James…
Dirty Data, some data fields contain bad data. i.e Intune phone numbers (restricted by operating systems and ownership.), personal devices enrolled by Intune (phones), and almost all the data in MFM.
G.James SNOW HAM has been customized to support the business, this coupled with financial constraints on the project makes available solutions potentially unfeasible. I.E Microsoft Graph.

## Slide 5: Stake Holders
Infrastructure Manager | Service Desk Manager | Service Desk Staff
Address “Close enough is good enough” concerning non existent models | Address “Close enough is good enough” concerning non existent models | Portable
Update all mandatory fields currently manually entered, for accurate data for reporting. | Import all devices including monitors and headsets ect.. | Simplistic use for Service Desk member
Populate last signed-in and date of last sign. Feature previously supplied by SCCM | Import purchase order numbers and costings | Minimal additional permissions or set up required.
Focus on Phones and computers with Intune as a source of truth for data to replicate from. |  | Minimal upkeep or support

## Slide 6: Sprints
Sprint 1 Objectives / Deliverables.
Map asset fields from SNOW and Intune.
Create a script that creates spreadsheets with the required Snow fields.
Add functionality to manage Phones and computers.
Add functionality to adjust mandatory fields in snow.
Add functionality to populate last logged-in and date.
Add error handling and portability.
Sprint 2 Objectives / Deliverables
Add functionality to include PO and Cost fields that are not currently populated.
Add functionality to include monitors from ‘HP Monitors Fleet Management project.’
Create Training and support material.
Sprint 3 Objectives / Deliverables
Add functionality to include Peripherals.
Add functionality to include Network Infrastructure.
Add functionality to include Audio Visual equipment

## Slide 7: Intune Snow asset Import Sprint 1
By Mathew Gallehawk
For: Darren Daly, Bruce Absolom, Joel Porgand

## Slide 8: Sprint 1 Overview
Deliverable | Requirements | Status
Map asset fields from SNOW and Intune. | Identify mandatory fields for SNOW bulk asset upload to be successful. Relate these to Intune device export fields. | Completed
Create a script that creates spreadsheets with the required Snowfields. | Script takes in Intune export fields and outputs SNOW bulk upload list and snow model update list | Completed
Add functionality to manage Phones and computers. | Focus is on Phones and Computers for this sprint. Script to create objects of computers and phones from Intune export file. | Completed
Add functionality to adjust mandatory fields in snow. | Script is to transform Intune fields to Snow fields. Where values cant be directly passed some transformation will be required. | Completed
Add functionality to populate last logged-in and date. | This functionality was formerly supplied by SCCM, has not been populated since the deactivation of SCCM. Not “Required for successful upload to SNOW. Stake holder would prefer this functionality from Microsoft if possible. | Functional, fields populate with the addition of a Sophos export. Have a ticket with Microsoft to see if this functionality is available without the usage of graph.
Add error handling and portability. | Terminate the app gracefully with an error message if the required export sheets are not present. Clean up old sheets so that old data does not get re-populated. Close all connections to AzureAd on close. Script and required folders should just unpack on a pc and work. | Completed
Create Training and support material | Document technical support. Document end-user setup and requirements. | Not yet Completed (Pushed over to sprint 2)

## Slide 9
Sophos Device Export
Name (Device Name)
Last logged on (User)
Last logged on Date
Intune device export CSV
Device Name
Serial Number
Manufacturer
Model
IMEI
Subscriber Carrier
Primary User
Ownership
OS
Phone Number
Asset Bulk Upload CSV (SNOW)
Serial Number
Asset tag
Model name
Model Display Name
Assigned To
Company
State
Owned By
Managed By
Support Group
Comments
Depreciated amount
Pre-allocated
Quantity
Resale price
Salvage price
Last logged on
Last log on date
Model category
Model Update CSV (SNOW)
Model Categories
Class
Manufacturer
Model Number
Owner
Status
Expenditure Type
Asset tracking strategy
Asset Tracking Unit
Transform Table |  |  | 
Data In Asset | Data out Asset | Data IN Model | Data Out Model
Serial Number (no transformation) | Serial Number | Model (Transformations for Some devices) | Model Categories
Device Name (Drops ‘Desktop’) | Asset tag | Hard coded = 'cmdb_hardware_product_model' | Class
Model (Transformations for Some devices) | Model name | Manufacturer | Manufacturer
Manufacturer + Device Name | Model Display Name | Model | Model Number
Primary User | Assigned To | Ownership (If Corporate = Ross) | Owner
Ownership (Corporate = G.James…) | Company | Hard coded = 'In Production' | Status
Hard code = in use | State | Hard coded = Capex | Expenditure Type
Ownership (If Corporate = Ross) | Owned By | Hard coded = 'Leave to category' | Asset tracking strategy
Ownership (If Corporate = Ross) | Managed By | Hard coded = 'Individual Unit' | Asset Tracking Unit
Hard code = 'ICT - Service Desk' | Support Group | Model | Name
IMEI + Subscriber Carrier + Phone Number | Comments |  | 
Hard code = 'AUD0.00' | Depreciated amount |  | 
Hard Code = False | Pre-allocated |  | 
Hard code = 1 | Quantity |  | 
Hard code = 'AUD0.00' | Resale price |  | 
Hard code = 'AUD0.00' | Salvage price |  | 
Last logged on (User) | Last logged on |  | 
Last logged on Date | Last log on date |  | 
OS (windows or Mac = computer, and some hard-coded mapping for current model devices) | Model category |  | 
Sprint 1 Data Mapping Table

## Slide 10: Sprint 1 Hard Code Transformations
Model Name
Lenovo's and a few phones only presented with a model number and not a model name.
These names are generated by correlating the model number to the model name on the vendor’s site, and hard-coding these values.
Ok for end-of-life Lenovos but will require ongoing support for other new devices that present in this way.
Model Category
Other than the operating system there is no apparent variable that would accurately correlate to this variable.
First-level filter devices buy the operating system. This defines them as ‘Mobile Handsets’ or Computers.
All devices that have current assignments of Workstation- Advanced ect have been coded to translate based on data already existing in snow.
To facilitate more categorisation than ‘Computer’ and phone, further updates will be required to this script every time a new model is added.
Owned by, Managed by, and Company
These values are translated from Personal or Corporate devices.
All corporate devices get the values of ‘Ross Lennox’ and ‘G.James ..’ respectively.
All personal devices get assigned personnel for these fields and are consequently excluded from the output data.
Comments
Did not have fields in Snow for phone carrier phone number and IMEI for devices that require it.
These values are concatenated nicely into a string builder and output in the comments to facilitate these fields.

## Slide 11: End user Process for Current Stage
Export a device list from Sophos and add it to the folder specified. (Requires Sophos access, a standard for service desk analysts)
Export a device list from Intune with all fields selected, and add it to the folder specified. (Requires Intune access, a standard for service desk analysts)
Run script
Navigate to: SNOW -> System Import sets -> Data sources ->Models import data source.
Append the current attachment with the output csv for the model update.
Check Format is CSV.
Select Load all records.
Select Transform
Navigate to: SNOW -> System Import sets -> Data sources ->Assets import data source.
Append the current attachment with the output csv for the Bulk Asset Update.
Check Format is CSV.
Select Load all records.
Select Transform

## Slide 12: Sprint 1 Testing
The script output files were tested in the Development Snow environment. Results were reviewed by Vijay the technical expert for ServiceNow.
Wins | Losses
Created non-existent hardware models and migrated the incorrectly assigned devices to appropriate fields. | Phone naming is not managed in Intune and will not be unique enough needs addressing.
Updates records of existing devices in SNOW, not duplicate | Concerns about the amount of Service Desk support required to map category types of laptop/workstations standard /advanced etc as without updating code new models will either be a Phone or a Computer.
Updating a blank field does not remove existing data | Still Utilising Sophos to populate “Last Logged in” and “Last Log in date’ fields.
All currently used fields, auto populated fields and Last user and last logged-on fields populate where data is available. | 
Does not upload personal devices or devices that have not deployed correctly. | 
Adds new assets correctly | 

## Slide 13: Sprint 1 Addressing Losses / Concerns
Phone Naming Issue
Currently most iPhones are named iPhone as this is the default setting and is not changed by us or the user, this populates to the Asset Tag which is intended to be unique.
This is the major issue and Vijay is happy to test in Production once this issue is resolved.
Mitigated
Hard coded the phone class devices to set Asset tag based on user name and Mobile Phone. This meets the unique variable requirement.
Proposed Solution
Manage names of phones in a similar way we manage computer names Intune.
Ongoing Support
Currently script contains over 300 lines of code.
Typically service desk members will not be required to have the proficiency to maintain this.
Increasing complexity and scope means more code and more areas to maintain.
Last user logged in fields & Last Logged on Date
No way to populate these fields from Microsoft without the use of Graph or third-party solutions, has been found yet by myself or Garry Poon.
Mitigation.
Currently utilizing a device export from Sophos.
Infrastructure has raised a ticket with Microsoft to ascertain an authoritative answer for this. (RITM0047022)
Microsoft’s Authoritative answer was negative, creating a task for the infrastructure team to produce an alternative solution. (RITM0047052)
Should the results provide a useful way forward will push this over to sprint two.

## Slide 14: Next Planned Steps
Create end-user documentation including support manual and use procedure.
Have a different service desk member test the procedure in Dev and identify user requirements i.e permissions and PowerShell modules.
Have work peer-reviewed by both business systems and Infrastructure.
Create a change task to bring to production.

## Slide 15: Project at close of Sprint 1 State vs Stake Holders Requirements
Requirement | Meets or Misses | Actions to address
Address “Close enough is good enough” concerning non existent models | Meets | Testing showed that snow accurately displayed the models for the iPhones 14 and the HP firefly, these where devices that are known to be assigned to iPhone 13 and fury book respectively.
Update all mandatory fields currently manually entered, for accurate data for reporting. | meets | Testing shows that all fields that are currently manually populated and fields that currently auto populate from SNOW do so correctly
Populate last signed-in and date of last sign. Feature previously supplied by SCCM | Meets/Misses | Currently this is functional using Sophos export however, Infrastructure want this data to come from Azure and I have not found a way forward with this so far that dose not involve graph. Further research is required. Have requested Garry Poon to contact Microsoft for official response.
Focus on Phones and computers with Intune as a source of truth for data to replicate from. | Meets | 
Import all devices including monitors and headsets ect.. | Misses | Currently the focus is on phones and computers, monitors will be incorporated upon completion of project and evaluation of provide data.
Import purchase order numbers and costings | Misses | Looking at using Intune autopilot for this, PO numbers are added against serial number, further work to look at incorporating costings
Portable | Meets | System can be un packed an run, no need for server or changing code of filenames.
Simplistic use for Service Desk member | Meets | Relatively simple process.
Minimal additional permissions or set up required. | meets | Few Permissions and modules required, these are required for other Service Desk tasks, therefore are standard and not additional.
Minimal upkeep or support | Misses | Currently hard coded variables will require maintenance or acceptance.

## Slide 16: Intune Snow asset Import Sprint 2
By Mathew Gallehawk
For: Darren Daly, Bruce Absolom, Joel Porgand

## Slide 17: Sprint 2 Overview
Deliverable | Requirements | Status
(Possible) Bring forward – Change manner of “Last logged on user” & “Last Log on Date ” being populated. |  | Not yet Started
Map fields provided from HP display monitor to SNOW fields. Consider any transformation that may be required. Consider Management of Asset tags |  | Not yet Started
Review methods of recovering PO numbers and costings for Serial numbers. |  | Not yet Started
Add functionality to upload and process the monitor assets |  | Not yet Started
Add functionality to upload and process PO fields and Cost fields |  | Not yet Started
Update supporting documentation |  | Not yet Started

## Slide 18
monitor device export CSV
Serial Number
HostName
HostIp
ModelNumber
DisplayStatus
Manufacturer
UserName
Asset Bulk Upload CSV (SNOW)
Serial Number
Asset tag
Model name
Model Display Name
Assigned To
Company
State
Owned By
Managed By
Support Group
Comments
Depreciated amount
Pre-allocated
Quantity
Resale price
Salvage price
Last logged on
Last log on date
Model category
Model Update CSV (SNOW)
Model Categories
Class
Manufacturer
Model Number
Owner
Status
Expenditure Type
Asset tracking strategy
Asset Tracking Unit
Transform Table |  |  | 
Data In Asset | Data out Asset | Data IN Model | Data Out Model
Serial Number (no transformation) | Serial Number | Model (Transformations for Some devices) | Model Categories
GJMO - + SerialNumber (Last 6 didgets) | Asset tag | Hard coded = 'cmdb_hardware_product_model' | Class
Model number (Transformations for Some devices) | Model name | Manufacturer | Manufacturer
Manufacturer + Device Name | Model Display Name | Model | Model Number
UserName | Assigned To | Ownership (If Corporate = Ross) | Owner
HostIp (internal network = corp) | Company | Hard coded = 'In Production' | Status
Hard code = in use | State | Hard coded = Capex | Expenditure Type
Ownership (If Corporate = Ross) | Owned By | Hard coded = 'Leave to category' | Asset tracking strategy
HostIp (internal network = corp) (If Corporate = Ross) | Managed By | Hard coded = 'Individual Unit' | Asset Tracking Unit
Hard code = 'ICT - Service Desk' | Support Group | Model | Name
N/A | Comments |  | 
Hard code = 'AUD0.00' | Depreciated amount |  | 
Hard Code = False | Pre-allocated |  | 
Hard code = 1 | Quantity |  | 
Hard code = 'AUD0.00' | Resale price |  | 
Hard code = 'AUD0.00' | Salvage price |  | 
UserName | Last logged on |  | 
Date of upload | Last log on date |  | 
Hardcode Monitor | Model category |  | 
Sprint 2 Data Mapping Table

## Slide 19: Hard Code Transformations
Model Name
Model name based off model number
Owned by, Managed by, and Company
These values are translated from Personal or Corporate devices.
All corporate devices get the values of ‘Ross Lennox’ and ‘G.James ..’ respectively.
All personal devices get assigned personnel for these fields and are consequently excluded from the output data.

## Slide 20: End user Process for Current Stage
Export a device list from Sophos and add it to the folder specified. (Requires Sophos access, a standard for service desk analysts)
Export a device list from Intune with all fields selected, and add it to the folder specified. (Requires Intune access, a standard for service desk analysts)
Export a device list from HP Display xxx with all fields selected, and add it to the folder specified. (Requires Intune access, a standard for service desk analysts)
Run script
Navigate to: SNOW -> System Import sets -> Data sources ->Models import data source.
Append the current attachment with the output csv for the model update.
Check Format is CSV.
Select Load all records.
Select Transform
Navigate to: SNOW -> System Import sets -> Data sources ->Assets import data source.
Append the current attachment with the output csv for the Bulk Asset Update.
Check Format is CSV.
Select Load all records.
Select Transform

## Slide 21: Sprint 1 Testing
The script output files were tested in the Development Snow environment. Results were reviewed by Vijay the technical expert for ServiceNow.
Wins | Losses
Created non-existent hardware models and migrated the incorrectly assigned devices to appropriate fields. | Phone naming is not managed in Intune and will not be unique enough needs addressing.
Updates records of existing devices in SNOW, not duplicate | Concerns about the amount of Service Desk support required to map category types of laptop/workstations standard /advanced etc as without updating code new models will either be a Phone or a Computer.
Updating a blank field does not remove existing data | Still Utilising Sophos to populate “Last Logged in” and “Last Log in date’ fields.
All currently used fields, auto populated fields and Last user and last logged-on fields populate where data is available. | 
Does not upload personal devices or devices that have not deployed correctly. | 
Adds new assets correctly | 

## Slide 22: Sprint 1 Addressing Losses / Concerns
Phone Naming Issue
Currently most iPhones are named iPhone as this is the default setting and is not changed by us or the user, this populates to the Asset Tag which is intended to be unique.
This is the major issue and Vijay is happy to test in Production once this issue is resolved.
Mitigated
Hard coded the phone class devices to set Asset tag based on user name and Mobile Phone. This meets the unique variable requirement.
Proposed Solution
Manage names of phones in a similar way we manage computer names Intune.
Ongoing Support
Currently script contains over 300 lines of code.
Typically service desk members will not be required to have the proficiency to maintain this.
Increasing complexity and scope means more code and more areas to maintain.
Last user logged in fields & Last Logged on Date
No way to populate these fields from Microsoft without the use of Graph or third-party solutions, has been found yet by myself or Garry Poon.
Mitigation.
Currently utilizing a device export from Sophos.
Infrastructure has raised a ticket with Microsoft to ascertain an authoritative answer for this. (RITM0047022)
Microsoft’s Authoritative answer was that negative, created a task for the business system to produce an alternative solution. (RITM0047052)
Should the results provide a useful way forward will push this over to sprint two.

## Slide 23: Next Planned Steps
Create end-user documentation including support manual and use procedure.
Have a different service desk member test the procedure in Dev and identify user requirements i.e permissions and PowerShell modules.
Have work peer-reviewed by both business systems and Infrastructure.
Create a change task to bring to production.

## Slide 24: Project at close of Sprint 1 State vs Stake Holders Requirements
Requirement | Meets or Misses | Actions to address
Address “Close enough is good enough” concerning non existent models | Meets | Testing showed that snow accurately displayed the models for the iPhones 14 and the HP firefly, these where devices that are known to be assigned to iPhone 13 and fury book respectively.
Update all mandatory fields currently manually entered, for accurate data for reporting. | meets | Testing shows that all fields that are currently manually populated and fields that currently auto populate from SNOW do so correctly
Populate last signed-in and date of last sign. Feature previously supplied by SCCM | Meets/Misses | Currently this is functional using Sophos export however, Infrastructure want this data to come from Azure and I have not found a way forward with this so far that dose not involve graph. Further research is required. Have requested Garry Poon to contact Microsoft for official response.
Focus on Phones and computers with Intune as a source of truth for data to replicate from. | Meets | 
Import all devices including monitors and headsets ect.. | Misses | Currently the focus is on phones and computers, monitors will be incorporated upon completion of project and evaluation of provide data.
Import purchase order numbers and costings | Misses | Looking at using Intune autopilot for this, PO numbers are added against serial number, further work to look at incorporating costings
Portable | Meets | System can be un packed an run, no need for server or changing code of filenames.
Simplistic use for Service Desk member | Meets | Relatively simple process.
Minimal additional permissions or set up required. | meets | Few Permissions and modules required, these are required for other Service Desk tasks, therefore are standard and not additional.
Minimal upkeep or support | Misses | Currently hard coded variables will require maintenance or acceptance.

## Slide 25: Intune Snow asset Import Sprint 3
By Mathew Gallehawk
For: Darren Daly, Bruce Absolom, Joel Porgand